## Sheet1
Requirement Details (IN SCOPE) | Status | Comment
2. Web Based Report Designer | Completed
a. Design | Completed
b. UI Design | Completed
c. Integrate with core system | Completed
d. Develop a UI and components to Connect the Database will be leveraged the connect string from Core system | Completed
e. Develop UI and Components for Table and Column Selection | Completed
f. Develop UI and Components for query Builders | Completed
g. Table Join should be manually identified by Users | Completed
h. Develop a UI and components for Report Viewer / Preview | Completed
i. Develop a UI and Components from Report View / preview – CSV, Export to Excel and open source Start office | Completed | Star Office Pending
j. Develop a UI and Components for Sort Order | Completed
k. Provide feature and interface to Save the reports | Completed
l. Provide feature for Submit a queue (Setup the Max limit on queue) | Inprogress | 2016-02-07
m. Provide an interface to schedule a reports with output storage location (FS) | Completed
n. Schedule options should be (Day wise, (Night or day), Timing) | Completed
o. Option to Send an Email to reports during the SAVE | Completed
q. Type of generation of reports would be - Schedule automatic when we rung the report, queued reports – background, instant reports – web view | Completed
r. The format should support would be Excel, Html and PDF | Completed
s. There is provision to Run report Now, if the execution time was more it should recommend user to submit a queue | Completed
3. Schedule a Reports | Completed
a. The scheduler Job will execute the reports in Background and CSV, Excel output will store in File Server | Completed
b. Report Scheduler - Web View | Completed
c. Submit a report to Queue and priority (High, Low and Normal) | Inprogress | 2016-02-07
d. When save the report to queue and define the name of the queue | Completed
e. UI and Components to Control - Start, Stop on the schedule a reports | Completed
f. UI and components to view the report Queue | Completed
g. UI and Components to view the Schedule Log status on each reports with Basic Filters | Inprogress | 2016-04-04
h. Queue management based on the settings | Completed
4. Report Viewer | Completed
a. iinterchange - Authorization integration | Completed
b. provision to hide and show the report during view | Inprogress | 2016-04-04
c. Select a report which are saved can be view | Completed
d. View the reports - Table format only | Completed
e. Export the reports in Excel | Completed